## Slide 1
Project Cycle Management for
International Development
Cooperation
RIVER Case history
Teacher
Pietro Celotti
Università degli Studi di Macerata
10 October 2011

## Slide 2: RIVER project
Before starting the analysis of proposal writing and project management disciplines, we will get familiar with one concrete project
Let us see the promotional dvd of the RIVER project

## Slide 3: Basic information
Programme: Culture 2007-2013 – Cooperation measures
Title: RIVER – Representing the Identities and the Voices of the European Riverains
Period: 1/10/2008 – 30/09/2010
Total estimated cost: 380.000
Total declared cost: 366.629.10

## Slide 4: Partnership
Lead partner: Provincia di Ancona (Local authority - IT)
Partner 1: AHE (Academy – PL)
Partner 2: CPPC (Governmental agency – RO)
Partner 3: KSL (NGO – FI)

## Slide 5: General aim
To evoke a common heritage of memories related to the river, to transform them into an occasion of European dialogue and to create new occasions of cultural socialisation in the natural environment of the river

## Slide 6: Specific aims
To let a group of European theatre directors meet and create a play based on the stories collected on each project's river (Esino – IT, Jasien - PL, Dâmboviţa - RO, Vantaa – FI)
To let groups of European young visual artists create installations along the project's rivers - being inspired to the RIVER stories, they shall be exploited as a set for the theatre performances

## Slide 7: Specific aims
To let young local actors perform the theatre play along the project's rivers - this shall encourage the intercultural dialogue among the European audiences in the involved different territories in order to underline the concept of European citizenship

## Slide 8: Stories collection
Collection of about 40 stories related to the project’s rivers:
    Esino (IT)
    Jasien (PL)
    Dâmboviţa (RO)
    Vantaa (FI)
Collection followed the same criterion in all countries

## Slide 9: Visual arts competition
Selection of 36 young visual artists:
    12 based in Italy
    12 based in Poland
    12 based in Romania
The rules of competition were the same in all countries and the artists were selected on a multidisciplinary basis

## Slide 10: Story writing workshops
4 performing artists (one per country) were committed to create a European play based on the rivers’ stories
Thanks to the “domino principle” they elaborated a play based on 8 stories (2 per river)
The title of the play is “Blue spaces”
In order to achieve this artistic result, the artists met in Jesi (IT) and Helsinki during 2009

## Slide 11: Story telling workshops
The RIVER’s performing artists were involved in 2 more workshops, aimed at exchanging information and practices for the production of the final performance in each country
The workshop of Lodz had to be dedicated to scenography
The workshop of Bucharest had to be dedicated to working with the actors
These workshops were not successful

## Slide 12: Visual arts workshops
Visual artists were expected to highlight the Dâmboviţa , Jasien and Esino rivers
In concrete, the creation of open air installations along the rivers was planned
The highest ambition of the project was to let the performing artists use the installations as sceneries for their performances

## Slide 13: Visual arts workshops
The first transnational visual arts workshop was organised in September 2009 along Dâmboviţa river in Cetateni, Romania
The territory was extremely rural and the intercultural dialogue between the artists and the local citizens was unexpectedly intensive

## Slide 14: Visual arts workshops
The second transnational visual arts workshop was organised in April 2010 along Jasien river in Lodz, Poland
The artists landed in Warsaw in the same day of the awful plane crash, which caused the death of president Kaczynski and of an important part of the Polish establishment
This was also the month of volcanic ash
The feature of this workshop was post-industrial

## Slide 15: Visual arts workshops
The third transnational visual arts workshop was organised in June 2010 along Esino river in Rosora, Italy
It was hinged on the relationship between the village (borgo) and the river
It produced extraordinary works that the municipality decided to keep permanently

## Slide 16: Final performances
Final performance in Helsinki (9/06/2010) followed a clownish style
Final performance in Cetateni (1/07/2010) was dedicated to the village’s children
Final performance in Maiolati Spontini (25/07/2010) happened IN the water of Esino
Final performance in Lodz (10/09/2010) was set in an abandoned factory covered by grass
UNITY IN DIVERSITY!

## Slide 17: Communication
Communication and dissemination are very important issues in each project co-funded by EU
In RIVER the communication strategy was based on:
    Dynamic website
    Public conferences, communication campaigns, newspapers’ articles
    Distribution of paper catalogue and dvd

## Slide 18: Project management
Cooperation between the partners was based on a partnership agreement
The project managers met 9 times (with several bilateral meetings!)
First meetings were very well reported
In the second part of the project there was a lower pressure but the activities continued regularly thanks to a shared project ownership

## Slide 19: Sustainability
In spite of such a successful project, sustainability risks to be a weak point:
    We have no information on the use of the European play “Blue spaces”
    Even in Italy, where the installations were preserved and collected in an exhibition space, there are no guarantees on the future fruition of such valuable works
    The network of artists risks to disappear

## Slide 20: You are the next!
I wish you become able to design and manage projects with a significant value:
    during the phase of co-funding
    after the phase of co-funding

## Slide 21
Remember the
Welcome lesson
of Wednesday
p.celotti@t33.it