## Slide 1
Project Cycle Management for
International Development
Cooperation
Logical Framework approach
Teacher
Pietro Celotti
Università degli Studi di Macerata
28 October 2011

## Slide 2: Analysis of the problems
The existing cause-effect relations (normally negative) are identified in a given situation. This exercise is aimed at:
    Identifying the object of the analysis
    Identifying the partners and stakeholders
    Identifying and building the hierarchy of the problems

## Slide 3: Problem tree
PROBLEM CONSEQUENCES
Current situation
PROBLEM
PROBLEM
Problem cause
Problem cause
Problem cause
Problem cause

## Slide 4: Problem tree
Mothers unwilling to attend clinics
Infrequent and inadequate coverage of clinics
Shortage of drugs
Low staff skills
Low attendance at rural clinics
Birth complications diagnosed late or not at all
High incidence of acute birth complications
High infant and maternal mortality rates
Low standards of hygiene and patient care by staff
High rates of post-partum and neo-natal infection
Commecial pressures to use milk supplements
Poor seasonal availability of high protein foods
Poor nutritional status of babies and infants
Few babies and infants vaccinated
High rates of infection among babies and infants
CAUSES
EFFECTS

## Slide 5: Analysis of objectives
This methodology allows:
      To describe the future scenarios deriving from the problems’ solution.
      To verify the objectives’ hierarchy.
      To clarify in a diagram the means-ends relations.
The negative situations identified in the problem
tree are transformed into positive and already
reached situations.

## Slide 6: Transformation of the problems into objectives
Problem
Objective
High infant and
maternal
mortality rates
Infant and maternal mortality rates reduced
High incidence of
acute birth
complications
Birth
complications
diagnosed
late or not at all
Reduced incidence of acute birth complications
Increased/earlier diagnosis of birth complications

## Slide 7: Objective tree
EFFECTS OF THE PROJECT
Expected situation
PURPOSE
PURPOSE
Results
Results
Results
Results

## Slide 8: Objective tree
Mothers willing to attend clinics
Increased and regular coverage by clinics
Sufficient drugs available
Improved staff skills
Attendance at rural clinics by mothers increased
Increased/earlier diagnosis of birth complications
Reduced incidence of acute birth complications
Infant and maternal mortality rates reduced
Standards of hygiene and patient care improved
Rates of post-partum and neonatal infection reduced
Increased proportion of babies breast-fed
Seasonal availability of high protein foods increased
Nutritional status of babies and infants improved
Increased N. of babies and infants vaccinated
Rates of infection among babies and infants reduced
MEANS
ENDS

## Slide 9: Analysis of possible strategies
The different groups of similar Objectives identified in the Problem tree become Strategies.
The most appropriate and feasible strategy is selected on the basis of different criteria (priority, budget, timing).
This phase requires therefore 2 steps:
    Identification of the different strategies allowing to reach the project’s purpose.
    Choice of the project’s strategy.

## Slide 10: Analysis of possible strategies
Mothers willing to attend clinics
Increased and regular coverage by clinics
Sufficient drugs available
Improved staff skills
Attendance at rural clinics by mothers increased
Increased/earlier diagnosis of birth complications
Reduced incidence of acute birth complications
Infant and maternal mortality rates reduced
Standards of hygiene and patient care improved
Rates of post-partum and neonatal infection reduced
Increased proportion of babies breast-fed
Seasonal availability of high protein foods increased
Nutritional status of babies and infants improved
Increased N. of babies and infants vaccinated
Rates of infection among babies and infants reduced
MEANS
ENDS
Nutrition strategy
Primary healthcare
strategy
Secondary healthcare
strategy

## Slide 11: Proposal formulation
Proposal design is facilitated by the Logical Framework (Logframe). This is a matrix allowing to organise the different elements of a proposal:
    Intervention logic
    Verifiable indicators
    Sources of verification
    Assumptions
Logical Framework is a methodology allowing to check if the intervention is properly structured. It supports the implementation of monitoring and evaluation actions.

## Slide 12: Logical framework
 | Intervention logic | Verifiable indicators | Sources of verification | Assumptions
Overall objectives |  |  |  | 
Project purpose |  |  |  | 
Results |  |  |  | 
Activities |  | MEANS | MEANS | 

## Slide 13: LF description
The column Intervention logic indicates the contents of the project.
The column Indicators gives the tools to verify if the objectives are reached and the results achieved.
The column Sources of verification indicates what information have to be used in order to apply the indicators.
The column Assumptions includes the external factors affecting (positively or negatively) the project’s impementation.

## Slide 14: Intervention logic
The following hierarchy is designed:
    GENERAL OBJECTIVES: long term benefits for the society.
    PROJECT PURPOSE: benefits for the project’s beneficiaries.
    RESULTS: concrete services/goods made available by the project.
    ACTIVITIES: how the project’s services/goods will be delivered.

## Slide 15: Vertical logic
If-then logic:
    If the ressources are provided then the activities can be performed.
    If the activities are performed then the results are produced.
    If the results are produced then the project’s puropose is achieved.
    If the project’s purpose is achieved then the general objective is pursued.

## Slide 16: Horizontal logic
Indicators specify how the achievement of objectives and results can be verified and measured.
They are established according to questions such as “How to realise if what I have planned has really happened or not?”
There are not indicators without sources of verification.

## Slide 17
LF is an effective planning and management tool – but not easy
p.celotti@t33.it