## Slide 1
Project Cycle Management for
International Development
Cooperation
Stakeholder analysis
Teacher
Pietro Celotti
Università degli Studi di Macerata
13 November 2012

## Slide 2: Logical Framework approach
1. ANALYSIS
Current situation is analysed in order to design the image of the future “desired situation”. It will facilitate the identification of the appropriate strategies in order to reach the desired situation.
Objective: to guarantee that the project idea is relevant to the future situation desired.
2. PLANNING
The project idea is specified in a plan.
Objective: to guarantee the development of the project.

## Slide 3: Logical Framework approach steps
PLANNING
LF Matrix
Activity scheduling
Resource scheduling
ANALYSIS
Stakeholder analysis
Problem analysis
Objective analysis
Strategy analysis

## Slide 4: Proposal writer, again
Identifying the project idea with relevant stakeholders
Analysing the funding programme
Creating the network of partners
Elaborating the proposal’s description
Elaborating the budget’s description
Checking the formal completeness of the proposal
“Managing” the proposal writing team
Sending the proposal by the deadline!

## Slide 5: Definition of Stakeholders
Any individuals, groups of people , institutions or firms that may have a significant interest in the success or failure of a project (either as implementers, facilitators, beneficiaries or adversaries)

## Slide 6: Steps for the analysis
Identifying the general development problem or opportunity being addressed/considered
Identify all those groups who have a significant interest in the (potential) project
Investigate their respective roles, different interests, relative power and capacity to participate
Identify the extent of cooperation or conflict in the relationships btw stakeholders

## Slide 7: Items of the analysis
The following information must be collected:
    Basic characteristics
    Interest and how affected by the problems
    Capacity and motivation to bring about change
    Possible actions to address stakeholders interests

## Slide 8
Cooperation projects are based on stakeholders’ involvement
p.celotti@t33.it