## Slide 1
Project Cycle Management for
International Development
Cooperation
Logical Framework tool
Teacher
Pietro Celotti
Università degli Studi di Macerata
25 October 2013

## Slide 2: Proposal formulation
Proposal design is facilitated by the Logical Framework.
This is a matrix allowing to organise the different elements of a proposal:
    Intervention logic
    Verifiable indicators
    Sources of verification
    Assumptions

## Slide 3: Proposal formulation
Logical Framework is a methodology allowing to check if the intervention is properly structured.
It supports the implementation of monitoring and evaluation actions.

## Slide 4: Logical framework
 | Intervention logic | Verifiable indicators | Sources of verification | Assumptions
General objective |  |  |  | 
Project purpose |  |  |  | 
Results |  |  |  | 
Activities |  | MEANS | MEANS | 

## Slide 5: LF description
The column Intervention logic indicates the contents of the project.
The column Indicators gives the tools to verify if the objectives are reached and the results achieved.
The column Sources of verification indicates what information have to be used in order to apply the indicators.
The column Assumptions includes the external factors affecting (positively or negatively) the project’s impementation.

## Slide 6: Intervention logic
The following hierarchy is designed:
    GENERAL OBJECTIVE: long term benefits for the society.
    PROJECT PURPOSE: benefits for the project’s beneficiaries.
    RESULTS: concrete services/goods made available by the project.
    ACTIVITIES: how the project’s services/goods will be delivered.

## Slide 7: Vertical logic
If-then logic:
    If the ressources are provided then the activities can be performed.
    If the activities are performed then the results are produced.
    If the results are produced then the project’s puropose is achieved.
    If the project’s purpose is achieved then the general objective is pursued.

## Slide 8: Horizontal logic
Indicators specify how the achievement of objectives and results can be verified and measured.
They are established according to questions such as “How to realise if what I have planned has really happened or not?”
There are not indicators without sources of verification.

## Slide 9: Intervention logic
Increased/earlier diagnosis of birth complications
Reduced incidence of acute birth complications
Infant and maternal mortality rates reduced
Standards of hygiene and patient care improved
Rates of post-partum and neo-natal infection reduced
Increased N. of babies and infants vaccinated
Rates of infection among babies and infants reduced
General Objective Level
Project purpose level
Results level
Activity level
OUT
1…..
Improved staff skills
Attendance at rural clins by mothers
Nutritional status of babies and infants improved
Increased and regular coverage by clinics
Mothers willing to attend clinics

## Slide 10: Identifying the objective
Once the Problem and Objective trees are designed and the possible strategies are identified, the project’s purpose (or specific objective) has to be chosen.
If only one specific objective or purpose is chosen, the project is clearer.

## Slide 11: Results, activities, assumptions
Once the specific objective and the relevant strategy are chosen, the means-ends relations must be analised again.
“Results” and “Activities” have to be inserted in the Logical Framework.
The elements that we have not inserted are out of the project. They can be considered as “assumptions”.

## Slide 12: Indicators and sources of verification
You will discuss wiht issue with my colleague Alessandro Valenza

## Slide 13: Assumptions
Assumptions are external factors, which will affect the project’s implementation and long-term sustainability but lie outside its control.
The probability and significance of these assumptions being met should be estimated as part of assessing the feasibility/riskiness of the project‏.

## Slide 14: Assumptions

## Slide 15: Our Logical Framework
Intervention logic
Indicators
Sources of indicators
Assumptions
General objective
To reduce infant/babies and maternal mortality rates in the country
Infant/babies mortality rate reduced from x to y from year 201.. to year 201..
Motallity rate of pregnant/taking care of children women reduced from x to y from year 201.. to year 201..
Stats of Health Ministry (ex ante, in itinere, ex post)
Project purpose
To reduce the rates of infection among babies and infant in the region of …
Rate of babies’ and infants’ infections reduced from x to y in hospitals and clinics concerned from year 201.. to year 201..
Data provided by hospitals and clinics concerned (ex ante, in itinere and ex post)
Results
Regular system of vaccination of infants and babies in 2 hospitals and 3 clinics located in the region of …
Improved nutritional status of infants and babies of monitored by 2 hospitals and 3 clinics located in the region of..
Number of under 5 babies vaccinated in hospitals and clinics concerned … increased from x% to y% from the year 201.. to year 201..
Number of under 5 babies properly fed in the region of … increased from x% to y% from the year 201.. to year 201..
Clinical data on vaccination provided every 3 months by hospitals and clinics concerned
Survey on the nutritional status of infants and babies in the region of …
Increased and regular coverage by clinics
Activities
1. To renovate the hospital’s and clinic’s equipment
2. To provide hospitals and clinics with ambulances dedicated to vaccination
3. To encourage mothers to breastfeed
4. To guarantee logistic for regular supply of high protein foods and drugs…
Technical assistance
Supply of equipment
Supply of drugs
Awareness campaign
Mantainance of equipment is guaranteed by local experts/companies

## Slide 16
LF represents the project in one page
p.celotti@t33.it