## Slide 1
Project Cycle Management for
International Development
Cooperation
Work plan
Teacher
Pietro Celotti
Università degli Studi di Macerata
8/11/2013

## Slide 2: Work plan
Are the activities sufficient to produce the expected results?
Are the latters identified as project milestones?
Are the activities feasible according to the project ressources?

## Slide 3: Work plan
Are the activities clearly referred to the partners in terms of responsibility?
Are the partners competent for the performance of such activities?

## Slide 4: Work plan
Are the activities well distributed during the project time?
Is there any exaggerated concentration of work for any of the partners?

## Slide 5: Work plan
Is the sequence of the activities analised?
Are emergency plans possible in case of unexpected difficulties?

## Slide 6: Work plan
Are the activities dedicated to project management properly envisaged?
Are the intermediate and final reports indicated as project milestones?

## Slide 7: Work plan
Are the activities dedicated to project communication/dissemination properly envisaged?
Does the dissemination strategy involve all partners and all territories?

## Slide 8
There are no results without activities, there are no activities without resources
p.celotti@t33.it